## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
1 | 1 | 1 | Load and clean the 50,000-review IMDb dataset by dropping missing values |  |  |  | Completed
1 | 1 | 2 | Store the raw, cleaned reviews in an SQLite database |  |  |  | Completed
1 | 1 | 3 | Apply text cleaning and normalization (lemmatization, stopword removal) to all reviews. |  |  |  | Completed
1 | 1 | 4 | Use multiprocessing to compute word counts from the cleaned text |  |  |  | Completed
2 | 2 | 5 | Implement sentiment analysis for all 50,000 reviews using TextBlob with multiprocessing |  |  |  | Completed
2 | 2 | 6 | Store TextBlob sentiment results (scores and labels) in the SQLite database |  |  |  | Completed
2 | 2 | 7 | Visualize TextBlob sentiment results (bar chart and histogram) |  |  |  | Completed
2 | 2 | 8 | Develop an automated email summary for the TextBlob analysis results |  |  |  | Completed
3 | 3 | 9 | Implement sentiment analysis using an LLM (DistilBERT) with GPU batch processing. |  |  |  | Completed
3 | 3 | 10 | Compare LLM vs. TextBlob performance (Accuracy and Processing Time) |  |  |  | Completed
3 | 3 | 11 | Generate confusion matrices for both LLM and TextBlob models to analyze error patterns |  |  |  | Completed
3 | 3 | 12 | Save all comparative analysis results (ground truth, LLM, TextBlob) to a final CSV file |  |  |  | Completed
3 | 3 | 13 | Update automated email to include the final comparative summary and Google Drive link |  |  |  | Completed
Note on F1: ====== ID#AAABcShYZQo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
Note on D2: ====== ID#AAABcShYZRI Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on E2: ====== ID#AAABcShYZRU Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on I3: ====== ID#AAABcShYZQ4 Sumeet Kumar Barua08 (2025-01-27 09:44:41) This is the total task estimated in hours for all the user stories
Note on J3: ====== ID#AAABcShYZRc Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 1 work
Note on K3: ====== ID#AAABcShYZRg Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 2 work
Note on L3: ====== ID#AAABcShYZQs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 3 work
Note on M3: ====== ID#AAABcShYZRo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 4 work
Note on N3: ====== ID#AAABcShYZQw Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 5 work
Note on O3: ====== ID#AAABcShYZRk Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 6 work
Note on P3: ====== ID#AAABcShYZRY Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 7 work
Note on Q3: ====== ID#AAABcShYZRA Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 8 work
Note on R3: ====== ID#AAABcShYZRs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 9 work
Note on S3: ====== ID#AAABcShYZRM Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 10 work
Note on T3: ====== ID#AAABcShYZRE Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 11 work
Note on U3: ====== ID#AAABcShYZQ8 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 12 work
Note on V3: ====== ID#AAABcShYZQ0 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 13 work
Note on W3: ====== ID#AAABcShYZRQ Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
1 | Sept 16, 2025 | Sequentially processing word counts for 50,000 reviews is too slow. | Implemented multiprocessing.Pool to parallelize text cleaning and word count computation across all CPU cores.
2 | Oct 3, 2025 | Need an efficient way to run a baseline sentiment analysis on the full dataset. | Used TextBlob combined with multiprocessing to quickly classify all 50,000 reviews. Stored results in SQLite for visualization.
3 | Oct 15, 2025 | TextBlob's accuracy is low (68.85%) and biased towards positive reviews. A more accurate model is needed | Implemented a DistilBERT LLM on GPU , which achieved 88.96% accuracy and showed balanced performance.
4 | Oct 16, 2025 | An attempt to parallelize the LLM using ThreadPool resulted in a critical accuracy drop to 58.90%. | Discovered that transformer models are not thread-safe. Replaced ThreadPool with batch processing, which fixed the accuracy (90.10%) and was 41.5x faster than CPU

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | 1 | 2025-09-14 | 2025-09-17 | Pratham R Shetty | Using multiprocessing.Pool for heavy CPU tasks | Running slow, sequential processing on large datasets. | Storing data in SQLite and applying text cleaning (lemmatization, etc.) | Confirm multiprocessing was successfully implemented for word counts.
2 | 2 | 2025-10-01 | 2025-10-04 | Pratham R Shetty | Visualizing sentiment results (bar charts, histograms). Automating email summaries | Only performing basic word counts. | Using multiprocessing for efficient analysis. Storing results in the database. | Benchmark the accuracy of TextBlob against a more advanced model.
3 | 3 | 2025-10-14 | 2025-10-17 | Pratham R Shetty | Using GPU-accelerated batch processing for LLMs. Benchmarking accuracy (88.96% vs 68.85%) | Using ThreadPool for LLMs (as it corrupted accuracy to 58.90%) | Comparing performance trade-offs (Accuracy vs. Speed). | Document the critical finding: Always use batch processing, not threading, for LLM inference